## Risk Management
Risk Assessment | [6 empty] | Risk Control
PR # | ID# : Title/Description | GxP Assessment - 21CFR11 Impact | Risk/Failure Scenarios | Severity | Probability | Risk Index | Risk Mitigation Steps | Verification of Mitigation Steps | S2 | P2 | RI2

## Risk Management Example
Risk Assessment | [7 empty] | Risk Control
PR # | ID# : Title/Description | GxP Assessment - 21CFR11 Impact | Risk/Failure Scenarios | Severity | Probability | Risk Index | GAMP5 | Risk Mitigation Steps | Verification of Mitigation Steps | S2 | P2 | RI2
DOM-50875, DOM-59966 | Unified Audit Trail | Yes |  |  |  |  | 5
| Event Tracker | Yes | Fails to track certain critical events due to configuration error. | High | Low | Medium | 5 | Implement automated configuration checks; conduct regular audits of tracked events. | Schedule automated alerts for configuration issues; perform monthly event audits. | Medium | Low | Low
| Event Tracker | Yes | Tracks too many non-essential events, leading to high storage use and potential performance impact. | Medium | High | Medium | 5 | Define event importance levels; set a policy to log only essential events. | Review and update event importance policy quarterly; conduct performance impact tests. | Low | Low | Low
| Event Capturer | Yes | Captures incorrect data, leading to inaccurate audit records. | High | Low | Medium | 5 | Add validation checks before capture; implement checks to verify the integrity of captured data. | Review audit logs monthly; conduct regular data integrity validation tests. | Medium | Low | Low
| Event Capturer | Yes | Data capture timing mismatch, leading to inaccurate timestamps. | Medium | Medium | Medium | 5 | Use synchronized system clocks; ensure timestamps are accurate to prevent time mismatches. | Run synchronization tests for system clocks; check timestamp accuracy in test cases. | Low | Low | Low
| Event Forwarder | Yes | Fails to forward events to storage, causing gaps in the audit trail. | High | Medium | High | 5 | Add retry mechanisms and real-time error notifications for forwarding failures. | Set up a monitoring dashboard for real-time tracking; conduct failure simulations. | Medium | Low | Low
| Event Forwarder | Yes | Sends duplicate events, leading to redundant entries. | Medium | Low | Low | 5 | Implement deduplication checks within the forwarding process. | Review logs weekly for duplicates; perform regular deduplication tests. | Low | Low | Low
| Event Storage | Yes | Storage system fails, leading to loss of audit data. | High | Low | Medium | 5 | Implement redundant storage with automatic failover; backup storage regularly. | Test failover monthly; schedule backup validation checks. | Medium | Low | Low
| Event Storage | Yes | Audit data becomes inaccessible due to corruption. | High | Low | Medium | 5 | Use data integrity checks and validation for stored records; employ error correction processes. | Conduct integrity validation tests periodically; implement automated corruption alerts. | Medium | Low | Low
| Event Querier | Yes | Unable to retrieve historical events due to query performance issues. | Medium | Medium | Medium | 5 | Optimize query performance through indexing; monitor and adjust database performance. | Set up performance monitoring; conduct query response time tests regularly. | Low | Low | Low
| Event Querier | Yes | Retrieves incomplete or inaccurate data due to query limitations. | High | Low | Medium | 5 | Implement validation checks for query results; define clear query requirements and test extensively. | Establish automated validation for query results; review sample queries monthly. | Low | Low | Low
| Event Exporter | Yes | Fails to export data for reporting, resulting in audit report delays. | Medium | Medium | Medium | 5 | Add error handling and retry mechanisms; notify admin upon export failures. | Check export logs for errors; conduct monthly mock export tests. | Low | Low | Low
| Event Exporter | Yes | Exports incomplete data, potentially omitting important events. | High | Low | Medium | 5 | Implement thorough validation checks before finalizing export; include data completeness checks. | Validate export completeness in test environment; schedule random checks of exports. | Low | Low | Low
DOM-57666 | Domino Flows Artifact Lineage | Yes |  |  |  |  | 4
| Artifact Definition | Yes | Incorrect artifact definitions by workflow authors, leading to misleading lineage information | High | Medium | High | 4 | Add validation for artifact definitions; provide guidelines for authors on correct definitions | Conduct regular audits of artifact definitions; include automated validation checks | Medium | Low | Low
| Artifact Definition | Yes | Missing artifacts due to incomplete definitions, leading to loss of data integrity | High | Low | Medium | 4 | Enforce mandatory fields for artifact definitions; notify authors on incomplete submissions | Review all artifact submissions periodically; set up mandatory fields in the UI | Medium | Low | Low
| Artifact Discovery | Yes | Artifacts fail to display in search results, leading to loss of accessibility for reuse | Medium | Medium | Medium | 4 | Implement a robust search indexing for artifacts; schedule periodic index refreshes | Test search results regularly; monitor user feedback on artifact accessibility | Low | Low | Low
| Artifact Bookmarking | Yes | Bookmarks not saved correctly, leading to issues in project-level displays | Medium | Medium | Medium | 4 | Implement confirmation step after bookmarking; add automated checks for bookmark persistence | Review bookmark logs weekly; run tests on bookmarking functionality periodically | Low | Low | Low
| Artifact Download | Yes | Code snippet fails to execute, causing download issues for workspace artifacts | High | Medium | High | 4 | Test snippet functionality across environments; add clear instructions for usage | Conduct cross-environment tests monthly; gather user feedback on download functionality | Medium | Low | Low
| Artifact Download | Yes | Downloaded artifacts are incomplete or corrupted | High | Low | Medium | 4 | Implement data integrity checks before download completion | Validate download integrity in staging environment; set up error alerts for failed downloads | Medium | Low | Low
| Lineage Tracking | Yes | Lineage information missing or incorrect, impacting traceability | High | Medium | High | 4 | Add lineage validation during artifact creation; provide lineage data testing tools | Regularly review lineage reports; schedule automated lineage integrity tests | Medium | Low | Low

## Risk Matrix
Risk Index |  | Severity |  |  |  | GAMP5 Category
|  | Low | Medium | High | Critical | Category | Detail
Probability | Critical | 2 | 3 | 4 | 4 | 1 | Operating Systems
| High | 1 | 2 | 3 | 4 | 3 | Standard Software
| Medium | 1 | 2 | 3 | 3 | 4 | Configured Software
| Low | 1 | 1 | 2 | 3 | 5 | Custom Software
Classification:
Risk Index | Definition
4 - Critical | Severe impact on operations, safety, compliance, or legal standing; potentially catastrophic. Requires immediate action, comprehensive mitigation plans, and top management involvement to prevent or address the risk. Must be addressed before release.
3 - High | Significant potential to disrupt operations, cause safety issues, or result in non-compliance. Demands prioritized attention, proactive mitigation strategies, and regular monitoring. Must be addressed before release.
2 - Medium | Potential to disrupt operations or cause moderate compliance issues. Requires targeted monitoring and preemptive measures to reduce the likelihood or impact. Should be addressed before release, can be addressed after release if a justifiable workaround is available and if release delay would lead to significant other problems. Mitigation plans must be communicated to appropriate personnel (including users).
1 - Low | Minimal impact on operations, safety, or compliance; easily managed if it occurs. Routine monitoring and standard procedures are sufficient to mitigate this risk. Does not block release of software for its intended use. Can be addressed in a future release, justification must be provided.